AI PR Security Review Agent — Implementation Plan

~14-week, single-squad delivery · Azure DevOps first · pragmatic hybrid (mapped to AI-200)

Approach: Build the thinnest end-to-end slice first (MVP walking skeleton), run it advisory-only, then add depth, policy and rollout. Ship value every 2 weeks. Keep analysis logic in portable OCI containers; use Azure PaaS for plumbing.

# Phased plan

| Phase | Timeline | Key work | Outcome / exit criteria |
| --- | --- | --- | --- |
| P0 Foundation | Wk 1–2 | Azure subscription, resource groups, IaC (Bicep), ACR, Key Vault, Entra managed identity, Azure OpenAI access approved, repo + CI skeleton. | Environments reproducible; OpenAI reachable via managed identity. |
| P1 MVP | Wk 3–6 | Functions webhook receiver → Service Bus → Container Apps orchestrator. Semgrep + secret scan. LLM triage (Azure OpenAI). Post summary + inline comments (advisory, non-blocking). | PR opened → comments appear automatically on a pilot repo. |
| P2 Depth | Wk 7–10 | Add CodeQL + Trivy (SCA) + basic IaC scan. RAG over OWASP/Bosch baseline (PostgreSQL + pgvector). Findings store (Cosmos DB), Redis cache, dedupe + severity scoring. | Lower false positives; richer, grounded findings; results persisted. |
| P3 Policy & rollout | Wk 11–14 | Per-service gating policy (App Configuration), waiver/override workflow, KQL dashboard, CD-09000 evidence feed, onboard 3–5 teams, enforce gate for sensitive services. | Configurable gate live; pilot teams onboarded; audit evidence flowing. |
| P4 Scale (next) | Wk 15+ | GitHub adapter, auto fix-suggestions, custom Bosch rule packs, false-positive feedback loop, broader rollout. | Multi-platform; continuous tuning; org-wide adoption. |

# Tech stack (hybrid)

Azure (managed): Functions, Service Bus, Container Apps + KEDA, Cosmos DB (vector), PostgreSQL/pgvector, Managed Redis, Key Vault, App Configuration, Entra ID, App Insights/Log Analytics, ACR, Azure OpenAI.

Portable (containers): Semgrep, CodeQL, Trivy, orchestration & LLM-reasoning logic (OCI images, runnable on self-hosted runners too). LLM kept behind a thin interface.

# Team & milestones

| Roles (small squad, ~3–4 people) | Milestones (demo every 2 weeks) |
| --- | --- |
| 1 Backend/Azure dev (AI-200 skills) | M1 (Wk2): infra up, OpenAI hello-world |
| 1 DevSecOps / pipelines | M2 (Wk6): MVP advisory review on pilot repo |
| 1 AppSec (rules, triage, validation) | M3 (Wk10): RAG + multi-scanner + dashboard |
| 0.5 Product/PM (scope, rollout, CD-09000) | M4 (Wk14): gating + 3–5 teams onboarded |

# First-week quick start

- Provision RG + Key Vault + ACR + Container Apps env via Bicep; wire Entra managed identity.

- Request/confirm Azure OpenAI deployment in an approved region; store keys in Key Vault.

- Stand up the Functions webhook receiver and an Azure DevOps service hook on one pilot repo.

- Run Semgrep in a container on a sample diff; post a hard-coded comment back to prove the loop.

Top risks to watch: false positives (keep advisory until tuned), LLM cost (cache + scope to diff), and IP/data residency (in-tenant Azure OpenAI only). Position the agent as a complement to annual pentest, not a replacement.

# Detailed plan to MVP (P0–P1, Weeks 1–6)

Three 2-week sprints. Estimates use story points (SP); 1 SP ≈ half a day. 'US' = user story. Goal of the MVP: a PR on a pilot repo automatically gets security comments — advisory only.

## Sprint 0 — Foundation (Weeks 1–2)

| US | User story | Acceptance criteria | SP |
| --- | --- | --- | --- |
| US-01 | As a platform engineer, I want the Azure environment provisioned via IaC so it is reproducible. | One Bicep deploy creates RG, ACR, Container Apps env, Service Bus, Key Vault, Entra managed identity; re-run is idempotent. | 5 |
| US-02 | As a platform engineer, I want Azure OpenAI reachable via managed identity so there are no static keys. | Model deployment in an approved region; a test call succeeds via managed identity; secrets only in Key Vault. | 3 |
| US-03 | As a developer, I want a CI skeleton that builds and pushes the container image to ACR. | Push to main builds the image, tags it, pushes to ACR; pipeline green. | 3 |
| M1 - Wk 2 | Infra up; Azure OpenAI hello-world works. | Demo: deploy from scratch + a successful model call. | 11 |

## Sprint 1 - Ingest & analyze (Weeks 3-4)

| US | User story | Acceptance criteria | SP |
| --- | --- | --- | --- |
| US-04 | As the agent, I receive Azure DevOps PR events via webhook so review starts automatically. | Service hook -> Functions receiver validates signature, enqueues a job on Service Bus; invalid signatures rejected. | 5 |
| US-05 | As the agent, I fetch the PR diff and changed files so I know what to scan. | Orchestrator (Container Apps) pulls the job, calls the Azure DevOps API, retrieves diff + file list; handles large diffs. | 5 |
| US-06 | As a developer, I want Semgrep and secret scanning run on the diff so known issues are flagged. | Scanner container runs on changed files; emits normalized findings (rule, file, line, severity) mapped to OWASP. | 5 |

## Sprint 2 - Reason & report (Weeks 5-6)

| US | User story | Acceptance criteria | SP |
| --- | --- | --- | --- |
| US-07 | As a security engineer, I want LLM triage of findings so noise is reduced. | LLM (Azure OpenAI) takes diff + findings and returns structured output: explanation, priority, likely-false-positive flag; it never overrides deterministic findings. | 5 |
| US-08 | As a developer, I want a summary plus inline comments on my PR so I can fix issues early. | Summary comment + inline comments (file/line, severity, fix hint) posted; an advisory (non-blocking) status check is set. | 5 |
| US-09 | As DevOps, I want basic run logs and metrics so I can see it working. | App Insights trace per run; success/failure and duration visible; failures raise an alert. | 3 |
| M2 - Wk 6 | MVP: advisory review live on a pilot repo. | Demo: open a PR, comments appear automatically. | 13 |

## Definition of Done (every US)

- Code reviewed and merged; runs in the deployed environment, not just locally.

- Secrets via Key Vault / managed identity - no hard-coded credentials.

- A basic test or a demonstrable end-to-end run; trace visible in App Insights.

- A short note in the README / runbook on how to operate or re-run it.

## Sequence & dependencies

US-01 -> US-02 / US-03 (infra first). US-04 -> US-05 -> US-06 (event before diff before scan). US-06 -> US-07 -> US-08 (findings before reasoning before posting). From Sprint 1 on, keep one pilot repo and one test PR as the constant feedback loop. Total to MVP: 37 SP across 3 sprints.